## Stakeholder Register
Stakeholder | Role / Interest | Power | Interest | Engagement Owner | Communication Method | Frequency | Notes
Buyers | Purchase & rate books | Low | High | Growth/Product | Email, in-app notifications | Weekly | Focus on UX and trust
Individual Sellers | List & sell used books | Medium | High | Seller Operations | Dashboard, email updates | Monthly | Need training & fair fees
Bookstores / Large Sellers | Sell in bulk, manage inventory | High | High | Partnership Manager | Account management meetings | Monthly | High influence
Traders / Swappers | Exchange books | Low | High | Community Manager | Forum & notifications | Ad-hoc | Need trust & safe trade workflow
Platform Admin / Product Owner | Ensure growth & system performance | High | High | Project Manager | Internal meetings & reports | Weekly | Decision maker
Payment Gateway | Process transactions | High | Medium | Engineering/Finance | SLA meetings & alerts | Quarterly | Critical to uptime
Logistics Partner | Deliveries & returns | High | Medium | Operations | Integration + SLA reports | Quarterly | Handle delays & returns
Customer Support | Resolve disputes & help users | Medium | High | Support Lead | Internal tools & sync meetings | Weekly | Need training & documentation
Legal / Compliance | Ensure laws, taxes, and IP rights compliance | High | Low | Legal Counsel | Compliance reports & approvals | Quarterly | Regulatory impact
Investors | ROI & platform growth | High | Medium | CEO / Product Owner | Performance dashboards & reports | Quarterly | Expect KPIs & financial results

## Power–Interest Matrix
Category | Stakeholders | Engagement Strategy
Manage Closely (High Power / High Interest) | Platform Admin, Large Sellers, Payment Gateway, Investors | Regular updates, one-on-one meetings, joint decisions
Keep Satisfied (High Power / Low Interest) | Legal / Compliance, Logistics Partners | Highlight key achievements, periodic reviews
Keep Informed (Low Power / High Interest) | Buyers, Individual Sellers, Customer Support, Traders | Frequent updates, community engagement
Monitor (Low Power / Low Interest) | Competitors, External Data Providers | Minimal communication unless needed

## Communication Plan
Stakeholder Group | Channel | Frequency | Message Focus | Responsible Party
Buyers | Email, in-app | Weekly | Promotions, reviews, trust updates | Growth/Product
Sellers | Dashboard, Email | Monthly | Sales performance, new features | Seller Operations
Admins / Investors | Reports, Meetings | Monthly/Quarterly | KPIs, financials, roadmap | Product Owner
Logistics & Payment Partners | Integration, SLA reports | Quarterly | Operational performance | Ops/Finance
Customer Support | Internal syncs | Weekly | Policies, issue tracking | Support Lead